## Timeline
Sequence | Pre-requisite | Task | Duration | Date | Planned Start Time | Planned End Time | Actual Start Time | Actual End Time | Status | Maker | Checker | Remarks
Pre-work
Assessment-01 | RRD file | RRD assessment | 1 Hour | 2023-08-09 | 13:00 | 13:30 | 14:00 | 14:30 | Completed | Karl Raymundo
Assessment-02 |  | CRQ Filing | 30 Mins | 2023-08-09 | 15:00 | 16:00 | 14:30 | 14:35 | Completed | Karl Raymundo
Drafting
Drafting-01 |  | Log in to Raven https://10.69.80.28:8443/LinkWorkbench | 2 Minutes | 2023-08-09 | 21:05 | 21:07 | 14:37 | 14:39 | Completed | Karl Raymundo | JP Tiburcio
Drafting-02 |  | Message Pattern Creation - Drafting and attributes | 2 Hours (Depends on how many MPs) | 2023-08-09 | 21:08 | 23:08 | 14:39 | 14:45 | Completed | Karl Raymundo | JP Tiburcio
Webtool Validation
Pre-Validation | RRD, WP, CXM, DCP, RSP (if available) | Message Pattern Name, ID, Spiel and Attributes Validation | 1 Hour (this is based on 10MPID only, testing will adjust depends on the count of MPIDs to be validated |  | 14:00 | 15:00 |  |  |  | Andre Galicha | Regina Rogelio
Implementation
Implem-01 |  | Log in to Raven https://10.69.80.28:8443/LinkWorkbench | 2 Minutes | 2023-08-17 | 21:00 | 21:02 | 21:05 | 21:06 | Completed | Karl Raymundo | JP Tiburcio
Implem-02 |  | Message Pattern Creation - Approving | 30 mins (Depends on how many MPs) | 2023-08-17 | 21:02 | 23:00 | 21:07 | 21:39 | Completed | Karl Raymundo | JP Tiburcio
Webtool Validation
Post-Validation | RRD, WP, CXM, DCP, RSP (if available) | Message Pattern Name, ID, Spiel and Attributes Validation | 1 Hour (this is based on 10MPID only, testing will adjust depends on the count of MPIDs to be validated | 2023-08-17 | 22:00 | 23:00 |  |  |  | Karl Lumabas | Regina Rogelio
Manual Push
SMS Notification | Test Number | Validate actual SMS Notification | 1 Hour (this is based on 10MPID only, testing will adjust depends on the count of MPIDs to be validated | 2023-08-18 | 9:00 | 10:00 |  |  |  | Karl Lumabas Alvin Mucho | Regina Rogelio

## Workplan
RAVEN ¦ WORKPLAN
[MESSAGE PATTERN CREATION]
P1 TM Additional Loan SKUs RR466
Prepared by: | John Paulo Tiburcio / Karl Raymundo | Prepared Date | 2023-08-09
Version | 1 | Implementation Date: | 2023-08-17
1. Go to Workbench> Communications > Message Patterns
2. Click Create New button
3. Enter Name, click Create then Edit Draft version
4. Add attributes on each Message Pattern
NOTE: Yellow Highlights means values should be taken from the RRD.
ATTRIBUTES
Immediate Delivery | No
Message Category | TRANSACTIONAL
Notification Enabled | Yes
Number Of Retries | 3
Primary Delivery Channel | SMS (over MAP)
Retry Settings | 1 atomic rule<30S, 1M, 2M>
Secondary Delivery Channel | SMS (over MAP)
Sender Mask | AutoLoadMAX
Activity Proper | Start/End Time | Estimated Duration | To be done by
1. Webtool Definition – Raven Webtool | 9:00 PM – 10:00 PM | 1 Hour | John Paulo Tiburcio
/ Karl Raymundo
2. Revert Plan | 10:00 PM – 11:00 PM | 1 Hour | John Paulo Tiburcio
· Expire message pattern or clone previous NPD brand, then approve. |  |  | / Karl Raymundo

## RRD
☐ | <----- Select 🗹 once done (automatic update on Gen Info)
<< GENERAL INFORMATION |  | OBJECTIVE OF THE BROADCAST | N/A
<< CUSTOMER JOURNEY |  | ESTIMATED VOLUME OF RECIPIENTS | N/A
|  | DESCRIPTION OF THE TARGET RECIPIENTS | TM
**(Please be specific. e.g. All active postpaid subscribers less Platinum, Corp, In-house accounts, opt-outs, hotlist)
|  | REQUIREMENTS AND MECHANICS | NEW (CAMPAIGN NAME) | MODIFY EXISTING (CAMPAIGN NAME) |  | MODIFY EXISTING (CAMPAIGN NAME)
|  |  |  | EXISTING | NEW | EXISTING | NEW
Campaign Duration
Delivery Hours (Window Period)
|  | Primary Channel(SMS/USSD) | SMS
Secondary Channel(SMS/USSD but you select SMS again)
|  | No. of retries (max of 3) | 3
|  | Retry Interval (max of 1 hr) | 30s, 1m, 2m
Frequency of delivery(ex. once per day or campaign)
|  | Sender/Mask Name per Brand (max 11 chars) | AutoLoadMAX
Whitelist
Target Location/Areas
|  | Location Identifier (email attachment of the list) | -Select One-
|  | TAC Codes (email attachment of the list) | -Select One-
|  | CallCard Numbers (email attachment of the list) | -Select One-
Special Instructions
|  | Message Category | Transactional
|  | Message Subcategory | N/A
Time to Live (TTL)
|  | Broadcast Message (Max of 512 Characters) | NEW (MESSAGE SCENARIO) | MODIFY EXISTING (MPID, MESSAGE SCENARIO)
|  |  |  | EXISTING | NEW
<Plan Name>
|  | Number of Characters: | 0 | 0 | 0
<Plan Name>
|  | Number of Characters: | 0 | 0 | 0
<Plan Name>
|  | Number of Characters: | 0 | 0 | 0
<Plan Name>
|  | Number of Characters: | 0 | 0 | 0
Brand |  | Messsage Pattern Name | AMAX successful registration message
Spiels
TM |  | AMAX_UTANG_P1ANS20 | Pwede mo nang magamit ang iyong hiniram na ANS20 na may 300MB pang-internet at 150MB para sa FunALIW apps. May unlimited calls at texts to all networks pa, lahat valid for 2 days! Para sa promo status, text UTANG ANS20 BAL to 3733. Pag may budget ka na, bumili lang ng at least P21 load para mabayaran at maka-avail muli ng Utang service na ito.
345
TM |  | AMAX_UTANG_P1FB10 | Pwede mo nang magamit ang iyong hiniram na FB10 with 600MB data pang-Facebook, valid for 3 days! Para sa promo status, text UTANG FB10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito.
261
TM |  | AMAX_UTANG_P1TIKTOK10 | Pwede mo nang magamit ang iyong hiniram na TIKTOK10 with 600MB data pang-TikTok, valid for 3 days! Para sa promo status, text UTANG TIKTOK10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito.
267
TM |  | AMAX_UTANG_P1YT10 | Pwede mo nang magamit ang iyong hiniram na YT10 with 600MB data pang-YouTube, valid for 3 days! Para sa promo status, text UTANG YT10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito.
260
TM |  | AMAX_UTANG_P1ML10 | Pwede mo nang magamit ang iyong hiniram na ML10 with 600MB data pang-Mobile Legends, valid for 3 days! Para sa promo status, text UTANG ML10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito.
267
TM |  | AMAX_UTANG_ANS20 90213 | From Pwede mo nang magamit ang iyong hiniram na UTANG ANS20 na may 300MB pang-internet at 150MB para sa FunALIW apps. May unlimited calls at texts to all networks pa, all valid for 2 days! Para sa promo status, text UTANG ANS20 BAL to 3733. Pag may budget ka na, bumili lang ng at least P24 load para mabayaran at maka-avail muli ng Utang service na ito.
To Pwede mo nang magamit ang iyong hiniram na ANS20 na may 300MB pang-internet at 150MB para sa FunALIW apps. May unlimited calls at texts to all networks pa, lahat valid for 2 days! Para sa promo status, text UTANG ANS20 BAL to 3733. Pag may budget ka na, bumili lang ng at least P24 load para mabayaran at maka-avail muli ng Utang service na ito.
CXM approval:
https://docs.google.com/spreadsheets/d/1kx-cj4O2ZDsf2vKLSpQyoJM6ZlrQAAKE0sw85IxROQA/edit?usp=sharing
Checking of existing spiels of SKUs

## SPIEL
TEST BED 1 https://10.66.9.88:4432/LinkWorkbench/ | TEST BED 2 https://10.237.196.74:4432/LinkWorkbench/ | PROD MPID | Message Name | Current Spiel | New Spiel | Status | Character Count
71273 | 35141 |  | AMAX_UTANG_P1ANS20 |  | Pwede mo nang magamit ang iyong hiniram na ANS20 na may 300MB pang-internet at 150MB para sa FunALIW apps. May unlimited calls at texts to all networks pa, lahat valid for 2 days! Para sa promo status, text UTANG ANS20 BAL to 3733. Pag may budget ka na, bumili lang ng at least P21 load para mabayaran at maka-avail muli ng Utang service na ito. |  | 345
71293 | 35161 |  | AMAX_UTANG_P1FB10 |  | Pwede mo nang magamit ang iyong hiniram na FB10 with 600MB data pang-Facebook, valid for 3 days! Para sa promo status, text UTANG FB10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito. |  | 261
71294 | 35181 |  | AMAX_UTANG_P1TIKTOK10 |  | Pwede mo nang magamit ang iyong hiniram na TIKTOK10 with 600MB data pang-TikTok, valid for 3 days! Para sa promo status, text UTANG TIKTOK10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito. |  | 267
71295 | 35201 |  | AMAX_UTANG_P1YT10 |  | Pwede mo nang magamit ang iyong hiniram na YT10 with 600MB data pang-YouTube, valid for 3 days! Para sa promo status, text UTANG YT10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito. |  | 260
71296 | 35202 |  | AMAX_UTANG_P1ML10 |  | Pwede mo nang magamit ang iyong hiniram na ML10 with 600MB data pang-Mobile Legends, valid for 3 days! Para sa promo status, text UTANG ML10 BAL to 3733. Pag may budget ka na, bumili lang ng at least P11 load para mabayaran at maka-avail muli ng Utang service na ito. |  | 267
71297 | 35221 |  | AMAX_UTANG_ANS20 | Pwede mo nang magamit ang iyong hiniram na UTANG ANS20 na may 300MB pang-internet at 150MB para sa FunALIW apps. May unlimited calls at texts to all networks pa, all valid for 2 days! Para sa promo status, text UTANG ANS20 BAL to 3733. Pag may budget ka na, bumili lang ng at least P24 load para mabayaran at maka-avail muli ng Utang service na ito. | Pwede mo nang magamit ang iyong hiniram na ANS20 na may 300MB pang-internet at 150MB para sa FunALIW apps. May unlimited calls at texts to all networks pa, lahat valid for 2 days! Para sa promo status, text UTANG ANS20 BAL to 3733. Pag may budget ka na, bumili lang ng at least P24 load para mabayaran at maka-avail muli ng Utang service na ito. |  | 345

## Validation
RAVEN PROD

## Test Bed
TEST BED 1 https://10.66.9.88:4432/LinkWorkbench/
TEST BED 2 https://10.237.196.74:4432/